## Sheet1
Defect/Enhancement: Defect ID | Subject | Functionality | Expected Result | Actual Result | Status | Testing Type | Severity
D-01799 | Observation#36:218828: CR#1418-Part2-Story#5-Create a Crosswalk Table to Map Max Supply Provision LVs to the Copay Strategy Option | HMO Medical | "Key" field should be unique as per the requirementÂ | User is able to create multiple records with same key field value Test Data:Â MS-07526 MS-07527 ETQA 08/16: Raised Now Karim 08/17: Should I go ahead and change the data type to text for the field â€œKeyâ€ on both crosswalks? Sushant 08/17: Can you please update it to â€˜Text' Karim 08/17: Requirement updated. Field type of key field is changed from formula to text, Mandatory is changed from "Unique" to "Unique No duplicates allowed" ETQA 08/18: Waiting for fix as per the requirement change ETQA 08/21: Retest partially pass. Key field is displayed on screen ADA 08/21: We have fixed Observation#36 in UAT. Key field has been removed from the layout. ETQA 08/21: Retest pass.Â | Closed | System Test | 2 - Medium
D-01800 | Observation#37:218829: CR#1418-Part2-Story#6-Create a Crosswalk Table to Map the Copay Strategy Options to the Option Details | Medicare - Part A | "Key" field should be unique as per the requirementÂ | User is able to create multiple records with same key field value Test Data:Â CSS-11009 CSS-11011 ETQA 08/16: Raised Now Karim 08/17: Should I go ahead and change the data type to text for the field â€œKeyâ€ on both crosswalks? Sushant 08/17: Can you please update it to â€˜Text' Karim 08/17: Requirement updated. Field type of key field is changed from formula to text ETQA 08/18: Waiting for fix as per the requirement change ETQA 08/21: Retest partially pass. Key field is displayed on screen. ADA 08/21: We have fixed Observation#37 in UAT. Key field has been removed from the layout. ETQA 08/21: Retest pass.Â | Closed | System Test | 1 - Low
D-01801 | Observation#32:218823: CR#1418-Part2-Story#1-Enhance CRD Builder Process to Support Contraceptive Copay | Traditional - PPO | 1) Fallout case Owner should be assigned to Case - BCT Supervisor Unassigned Cases 2) The below Error message should be populated in the error description under CRD Builder Fallouts section | 1) Fallout case Owner is assigned to CB_AdminQ 2) The below Error message is NOT getting populated in the error description under CRD Builder Fallouts section Data: CBON-567590 ¦ CRD-0943042 ¦ FC: 04393937 ETQA 08/09: Raised Now ETQA 08/15: Waiting for Code fix ADA 08/16: Observation#32 has been fixed. ETQA 08/17: Retest is in progress ETQA 08/20: Retest Partially Pass The error message is incorrect. Please help to resolve this Expected Error message: Max Supply provision crosswalk mapping should be added for the following Drug Lists: DL-0001425(Mail) ,DL-0001421(Mail) ,DL-0001419(Mail) ,DL-0001415(Mail) ,DL-0001428(Mail) ,DL-0001426(Mail) ,DL-0001423(Mail) ,DL-0001417(Mail) , to continue coding the CRD. Actual Error message: Max Supply provision crosswalk mapping should be added for the following DLs: DL-0001425(Mail) ,DL-0001421(Mail) ,DL-0001419(Mail) ,DL-0001415(Mail) ,DL-0001428(Mail) ,DL-0001426(Mail) ,DL-0001423(Mail) ,DL-0001417(Mail) , to continue coding the CRD. Test Data: CBON-567990 ¦ FC: 04394556 ADA 08/20: Fixed ETQA 08/20: Comma needs to be corrected in the error description in the fallout as per the requirementÂ Test Data: CBON-568021 ETQA 08/20: Retest Pass. Closed Test Data: CBON-568122 | Closed | System Test | 3 - High
D-01802 | Observation#52:218825: CR#1418-Part2-Story#3-Add New Fields on Drug Coverage Drug List(DCDL) | HMO - EPOs | 1) Following fields should be displayed in CRD HT PDF, CRD Record Tracker PDF Â after xml is Sent Â to CVS for Manual CRD and Builder CRD *Contraceptive Copay Strategy, *Steps, *Multipliers 2) Following fields should not be getting displayed in CRD Excel After xml is Sent to CVS for Manual CRD and Builder CRD *Contraceptive Copay Strategy Option | 1) Following fields are not getting displayed in CRD HT PDF, CRD Record Tracker PDF Â after xml is Sent Â to CVS for Manual CRD and Builder CRD *Contraceptive Copay Strategy, *Steps, *Multipliers 2) Following fields is getting displayed in CRD Excel After xml is Sent to CVS for Manual CRD and Builder CRD *Contraceptive Copay Strategy Option Test Data:Â CRD-0943769 - CRD Record Tracker, CRD Excel for Manual CRDÂ CRD-0943783 - CRD HT PDF for Manual CRDÂ CBON-568185 - CRD Record Tracker, CRD Excel for Builder CRDÂ CBON-568200 - CRD HT PDF for Builder CRD ETQA 08/22: Raised Now ADA 08/22: Part 1 is Invalid. Part 2 has been fixed. ETQA 08/22: Observation #52: Â As per the requirement, Contraceptive Copay Strategy Option field should not be displayed in CRD Record Tracker PDF. But it is getting displayed. Help us to resolve the same.Â ADA 08/23: The mentioned changes have been made. Components Modified: CRD â€“ New Record Tracking Template. ETQA 08/23: Retest Pass. | Closed | System Test | 2 - Medium
D-01803 | Observation#41218824: CR#1418-Part2-Story#2-Enhance CRD Wizard to Process Contraceptive Copay Strategy for New Manual CRDs | Traditional - POS | Alignment of the Warning message in Drug Coverage page Â should be in correct format | Alignment of the Warning message in Drug Coverage page Â is Â not in correct format Test Data: CRD-0943441 ¦ DC-1290699 -Retail Non-Commercial formulary Â -FRM-0012122 Commercial formulary Â -FRM-000031 ETQA 08/16: Raised Now ADA 08/21: Code fixed ETQA 08/21: Retest Yet to Start ETQA 08/22: Retest Pass. Closed ETQA 08/30 : Reopened. A bar is visible. AD 08/31 : It has been customized to accommodate future warning message if any. | Closed | Regression Test | 1 - Low
D-01804 | Observation#23:225980: CR#1418-Part2-Story#7-Enhance CRD Wizard to Process Contraceptive Copay Strategy forExisting CRDs | Medicaid | All the Contraceptive Copay Strategy fields Â should copy from existing CRD | Contraceptive Copay Strategy logic is not applying for cloned CRDs Data: Existing: CRD-0942988 ¦ Cloned CRD: CRD-0943037 ETQA 08/09: Raised Now ADA 08/09: Can you let us know if CRD Cloning was in scope/As a part of which request is CRD cloning in scope? We have made changes only for the DC and DCDL cloning. If yes, we would require a note in the story. Vinod 08/09: please review Observation 23 for now Karim 08/09: Can you please elaborate on Observation#23? Did you clone a manual or an automated CRD? Any of CCS fields/ parts cloned or none of the fields was cloned? ETQA 08/10: This Observation is regarding cloning the manual CRD but CCS related any of the fields are not cloned to the new CRDW Karim 08/10: Based on the requirements captured in Stories #3 and #4 all the newly created field for CCS should be cloned along with the other CRD fields. ADA 08/13: Fixed ETQA 08/13: Retest in progress ETQA08/14: Retest Pass. Closed Test Data: CRD-0943316 | Closed | Smoke Test | 2 - Medium
D-01805 | Observation#42:218824: CR#1418-Part2-Story#2-Enhance CRD Wizard to Process Contraceptive Copay Strategy for New Manual CRDs | Traditional - POS | Apply Limitations is set to "No" when Default Drug Â Group(DCA-0000648) is added back to DCDL Section | Apply Limitations is set to "Blank" when Default Drug Â Group(DCA-0000648) is added back to DCDL Section Test Data: CRD-0943460 ETQA 08/16: Raised Now AD 08/16: Â Invalid. For Provision 5 multi month Line values, thereâ€™s no mapping values in the system which states to set Apply Limitations to â€˜Noâ€™ for DCA-0000648 Drug Group.Â ETQA 08/17: Business should confirm on this Business 08/17: Observation#42 needs a code fixÂ ADA08/20: Fixed ETQA08/21: Retest Pass Test Data: CRD-0942410 DC-1288556 ¦ DCDL-45804786 DC-1288558 ¦ DCDL-45804916 | Closed | System Test | 2 - Medium
D-01806 | Observation#22:218825: CR#1418-Part2-Story#3-Add New Fields on Drug Coverage Drug List (DCDL) | HMO - EPOs | As per requirements Steps 1 to Step 12 and Multiplier1 to Multiplier12 fields should have read only Â access | Steps 1 to Step 12 and Multiplier1 to Multiplier12 fields in DCDL section having Â Edit Access Test Data: CRD-0942958 ¦ DC-1289712 ¦ DCDL-45747127 ETQA 08/09: Raised Now ADA 08/09: Fixed QA 08/10: Retest Pass | Closed | System Test | 2 - Medium
D-01807 | Observation#54:225980: CR#1418-Part2-Story#7-Enhance CRD Wizard to Process Contraceptive Copay Strategy for Updating Existing CRDs | Medicaid | As per the requirement, system should display the following error message The Contraceptive Copay Strategy field cannot be set to Applies on the DCDL if the field Does Contraceptive Copay Strategy Apply? is set to No on Drug Coverage | User is getting the below error message The Contraceptive Copay Strategy field cannot be set to Applies on the DCDL if the field Does Contraceptive Copay Strategy Apply is set to No on Drug Coverage Steps to recreate: - Create a DC record with â€œDoes Contraceptive Copay Strategy Apply? as â€œNoâ€ - Click on New DC Drug List/Group and create a DCDL record with Contraceptive Copay Strategy as â€œAppliesâ€ ETQA 08/24: Raised Now ADA 08/27: Fixed ETQA 08/27: 'the' is missing in the error message ADA 08/27: Fixed ETQA 08/27: Retest Pass | Closed | System Test | 1 - Low
D-01808 | Observation#30:218824: CR#1418-Part2-Story#2-Enhance CRD Wizard to Process Contraceptive Copay Strategy for New Manual CRDs | Traditional - HNO | Below Fields Â should Â updated with Mapping values of provision 5 line values in DCDL sectionÂ Inclusion/ExclusionÂ Inclusion/Exclusion Drug Class Apply Limitations | Below Fields Â not Â updated with Mapping values of provision 5 line values in DCDL sectionÂ Inclusion/ExclusionÂ Inclusion/Exclusion Drug Class Apply Limitations Test Data: CRD-0943280 ¦ Provision 5 Line Value - 197 | Closed | System Test | 2 - Medium
D-01809 | Observation#55:218823: CR#1418-Part2-Story#1-Enhance CRD Builder Process to Support Contraceptive Copay | Traditional - PPO | CBON should NOT get processed and user should get the same fallout message in Build Stage | CBON is getting processed till Build Stage and user is NOT getting the same fallout message Test Data: CBON-568471 ¦ FC: 04395352 Steps to recreate: - Create a CBON with below fallout "Max Supply Provision needs to be updated for the Contraceptive Copay Strategy to continue coding the CRD." P5LV199 - Contraceptive Copay Strategy - Applies P6LV123 - There is no active entry in (CCS-Max Supply Crosswalk) - Click on Continue Automation without creating a valid entry in Contraceptive Copay strategy - Max Supply crosswalk ETQA 08/24: Raised Now ADA 08/28: Fixed ETQA 08/28: Retest Pass. Closed Test Data: CBON-568704 ¦ FC: 04395661 | Closed | Smoke Test | 1 - Low
D-01810 | Observation#16:218825: CR#1418-Part2-Story#3-Add New Fields on Drug Coverage Drug List (DCDL) | HMO - EPOs | Contraceptive Copay Strategy Option xmltag should not display in CRDXML file | Contraceptive Copay Strategy Option xmltag is displaying in CRDXML file <Contraceptivecopaystrategy>CCS-00001</Contraceptivecopaystrategy> Test Data: CRD-0942857 CRD-0942857.xml ETQA 08/07: Raised Now ADA 08/07: Fixed Components modified: GMF_XML_CRD_controller QA 08/07: Retest Pass. Closed Test Data: CRD-0942937 | Closed | Regression Test | 2 - Medium
D-01811 | Observation#1:218823: CR#1418-Part2-Story#1-Enhance CRD Builder Process to Support Contraceptive Copay | Traditional - HNO | CRD should get created successfully | CRD is NOT getting created successfully Test data: CBON-567234Â ETQA 08/01: Raised Now ADA 08/02: Fixed QA 08/02: Retest Pass Test Data: CBON-567465 Â | Closed | System Test | 3 - High
D-01812 | Observation#2: 218823: CR#1418-Part2-Story#1-Enhance CRD Builder Process to Support Contraceptive Copay | Traditional - PPO | CRD should get created with formulary | CRD is created without formulary Test data: CBON-567236Â ETQA 08/01: Raised Now ADA 08/02: Fixed QA 08/02: Retest Pass Test Data: CBON-567465 | Closed | System Test | 2 - Medium
D-01813 | Observation#40:218825: CR#1418-Part2-Story#3-Add New Fields on Drug Coverage Drug List(DCDL) | HMO - EPOs | DC Record should get updated when other field values are edited | User is getting the below error message and user is NOT able to save the DC record Error message: Error: Invalid Data.Â Review all error messages below to correct your data. Contraceptive Copay Strategy Apply : Field is required Steps to recreate: Create a CRD with Drug Coverage record Open the DC record in Standard layout screen and edit the Override Refill Too Soon? field value Click on Save button ETQA 08/16: Raised Now ETQA 08/20: Need to be discussed in Today's Triage Triage 08/20: Needs to be discussed in Grooming call ADA 08/21: â€˜Does the contraceptive apply?â€™ field validation has been removed as discussed in grooming. For wizard validation rule we are waiting for Jenniferâ€™s comments. Business 08/22: Requirement updated ETQA 08/22: Retest Pass | Closed | System Test | 2 - Medium
D-01814 | Observation#26:218823: CR#1418-Part2-Story#1-Enhance CRD Builder Process to Support Contraceptive Copay | Traditional - HNO | Does Contraceptive Copay Strategy Apply? field value should be populated as "No" | Does Contraceptive Copay Strategy Apply? field value should be populated as BLANK Test Data: CBON-567666 ¦ CRD-0943128 ¦ Provision 5 Line Value 179 ETQA 08/10: Raised Now ADA 08/10: Obsevation#26 has been fixed. ETQA 08/10: Retest Pass. Closed Test Data: CBON-567666 | Closed | System Test | 3 - High
D-01815 | Observation#33:218824: CR#1418-Part2-Story#2-Enhance CRD Wizard to Process Contraceptive Copay Strategy for New Manual CRDs | Traditional - POS | Does Contraceptive Copay Strategy Apply Â values as "No" in standard layout pages then below fields are Â should not allow the user to populate values Provision 5 Line Value Max Supply Provision Max Supply Line Value | When Â user enter the Does Contraceptive Copay Strategy Apply Â values as "No" in standard layout pages then below fields are able to populate values Provision 5 Line Value Max Supply Provision Max Supply Line Value ETQA 08/14: Raised Now ETQA 08/14: Karim needs to update the Requirement ETQA 08/14: We have expectation behavior of Â Contraceptive Copay Strategy fields values in Drug coverage Wizard Visual Force and Drug coverage standard layout pages to be sameÂ ADA 08/14: In grooming we have discussed that the fields can be hidden only for visual force pages not for standard layouts. As salesforce doesnâ€™t provide conditional field control on the standard layouts ADA 08/16: Observation#33 has been fixed as per new Acceptance Criteria#12 for Story 7 ADA08/16: Fixed EQA:08/16: Retest Pass Test Data: CRD-0943441 | Closed | System Test | 3 - High
D-01816 | Observation#29:225980: CR#1418-Part2-Story#7-Enhance CRD Wizard to Process Contraceptive Copay Strategy forExisting CRDs | Medicaid | Does the Contraceptive Copay Strategy Apply Â should set as "No" for all existing CRD as per the requirement | Does the Contraceptive Copay Strategy Apply is set as "Blank" for all existing CRD Test Data: CRD-0942336 ¦ DC-1288411 ¦ DC-1288412 Acceptance Criteria#1: User ability to apply the Program Given that the user has accessed an existing CRD and is on Drug Coverage record in edit mode When the user updates the field "Does the Contraceptive Copay Strategy Apply?" from 'No' to 'Yes' Then the system should display and require user to populate the following fields: 1. Provision 5 Line Value 2. Max Supply Provision 3. Max Supply Line Value ETQA 08/13: Raised Now Vinod 08/13: Karim â€“ can you please confirm requirement for observation #29? ETQA08/14: Waiting for Karim's update for the Story 7 Karim 08/20: Requirement has been updated | Closed | Smoke Test | 2 - Medium
D-01817 | Observation#3:218824: CR#1418-Part2-Story#2-Enhance CRD Wizard to Process Contraceptive Copay Strategy for New Manual CRDs | Traditional - HNO | Drug Coverage record should get created in Wizard screen | Drug Coverage record is NOT getting Â created in Wizard screen. refer the screenshot Test data: CRD-0942544 ETQA 08/01: Raised Now ADA 08/02: Fixed QA 08/02: Retest Pass Test Data: CRD-0942880 ¦ DC-1289554 | Closed | System Test | 2 - Medium
D-01818 | Observation#4:218823: CR#1418-Part2-Story#1-Enhance CRD Builder Process to Support Contraceptive Copay | Traditional - PPO | Drug Coverage record should get created in Wizard screen | Drug Coverage record is NOT getting Â created in Wizard screen. Refer the screenshot ETQA 08/01: Raised Now Aditya 08/03: We are done with the Provision 5 Mapping data load in UAT.Â Please proceed. QA 08/06: Retest - Partially Pass. The below New LV's are NOT loaded in the system 200, 222, 223 ADA 08/07: In progress ADA 08/10: LV224 has been loaded to the system QA 08/10: Retest Pass. Closed ETQA & QA 08/30:Â Expected Result:Â â€¢ Drug List, â€œDL-0016570â€ - Notes section should be updated as â€œDL-0016570 - HCR- Contraceptive coverage Standardâ€ for Provision 5 line values 197, 198, 199, 202, 203, 204, 205, 206, 207, 208, 209, 211, 219, 222, 223, 224 -Fixed. â€¢ Drug Group â€œDCA-0000648â€ - Notes section should be updated as â€œDCA-0000648 - Contraceptives- all drugs and devices (Covered)â€ for Provision 5 line values 197, 198, 199, 202, 203, 204, 205, 206, 207, 208, 209, 211, 219, 222, 223, 224-Fixed. â€¢ Drug List â€œDL-0109016â€ â€“ Notes section should be updated as â€œDL-0109016 - HCR- Contraceptive coverage Standard PLUS 12 month supplyâ€ for Provision 5 line value 199 -Already this is the result Actual Result: â€¢ Drug List, â€œDL-0016570â€ - Notes section is updated as â€œDCA-0000648 - Contraceptives- all drugs and devices (Covered)â€ incorrectly for Provision 5 line values 197, 198, 199, 202, 203, 204, 205, 206, 207, 208, 209, 211, 219, 222, 223, 224 â€¢ Drug Group â€œDCA-0000648â€ - Notes section is updated as â€œDL-0016570 - HCR- Contraceptive coverage Standardâ€ incorrectly for Provision 5 line values 197, 198, 199, 202, 203, 204, 205, 206, 207, 208, 209, 211, 219, 222, 223, 224 â€¢ Drug List â€œDL-0109016â€ â€“ Notes section is updated as â€œDL-0118427 - HCR- Contraceptive Standard, WITH coverage of male condoms $0 after DED-12 monthâ€ incorrectly for Provision 5 line value 199 ETQA 08/31:Â Expected:Â â€¢ Drug List â€œDL-0109016â€ â€“ Notes section should be updated as â€œDL-0109016 - HCR- Contraceptive coverage Standard PLUS 12 month supplyâ€ for Provision 5 line value 199 -Already this is the result â€“In mail record (MV-0370269) â€¢ DL-0016570 â€“ Notes should be updated as â€œDL-0016570 - HCR- Contraceptive coverage Standardâ€ Actual: â€¢ Drug List â€œDL-0109016â€ â€“ Notes section is updated as â€œDL-0118427 - HCR- Contraceptive Standard, WITH coverage of male condoms $0 after DED-12 monthâ€ for Provision 5 line value 199 -Already this is the result â€“ In mail record (MV-0370269) â€¢ DL-0016570 â€“ Notes should be updated as â€œDL-0016570 - HCR - Contraceptive coverage Standardâ€ (Space before Â â€˜-â€˜ and there is 2 space after the â€˜-â€˜) ADA 08/31: Fixed ETQA 08/31: Retest Pass. Closed | Closed | Smoke Test | 2 - Medium
D-01819 | Observation#44:218824: CR#1418-Part2-Story#2-Enhance CRD Wizard to Process Contraceptive Copay Strategy for New Manual CRDs | Traditional - POS | Error Â message Â should display as per requirement Â below Set the field 'Does the Contraceptive Copay Strategy Apply?' to No or update the field 'Provision 5 Line Value' to continue Â | Error Â message Â is displaying Â as below in both pages Set the field Does the Contraceptive Copay Strategy Apply? to No or update the field Provision 5 Line Value to continue ETQA 08/17: Raised Now AD 08/20: Fixed the Code ETQA 08/20: Retest Pass ETQA 08/21: We are facing Error in Wizard Drug coverage screen when click save next button Â as below, Record ID :Cannot specify id in an insert call AD 08/21: Fixed the ObservationÂ ETQA 08/21: Retest Pass | Closed | System Test | 1 - Low
D-01820 | Observation#56:218823: CR#1418-Part2-Story#1-Enhance CRD Builder Process to Support Contraceptive Copay | Traditional - PPO | Fallout case should be updated with Multimonth logic Fallout Error: Max Supply Provision needs to be updated for the Contraceptive Copay Strategy to continue coding the CRD. | CBON is processed till Build stage and There is no updated error message based on Multimonth Test Data: CBON-568524 ¦ FC: 04395439 ¦ P6L5 which is inactive in CCS-Max Supply crosswalk Steps to recreate: - Create a CBON with Sensitive Client Build stage fallout - Click on Continue Automation ETQA 08/24: Raised Now ADA 08/28: Fixed ETQA 08/28: Retest Pass. Closed Test Data: CBON-568710 ¦ FC: 04395662 | Closed | Regression Test | 3 - High
D-01821 | Observation#19:218829: CR#1418-Part2-Story#6-Create a Crosswalk Table to Map the Copay Strategy Options to the Option Details | Medicare - Part D | field "Key" shouldn't be displayed on the screen.Â | field "Key" is displayed on the screen. Test data: CCS-11005 ETQA 08/07: Raised Now ADA 08/07: FixedÂ QA 08/07: Retest pass. Closed | Closed | System Test | 2 - Medium
D-01822 | Observation#6:218828: CR#1418-Part2-Story#5-Create a Crosswalk Table to Map Max Supply Provision LVs to the Copay Strategy Option | HMO Medical | Line Value Text, Drug List Name, Active, Comment - fields should be available in the Contraceptive Copay Strategy-Max Supply table | Line Value Text, Drug List Name, Active, Comment - fields are NOT available in the Contraceptive Copay Strategy-Max Supply table ETQA 08/02: Raised Now Aditya 08/02: Observation#06, 07, 08 are fixed in UAT. Please proceed. ETQA 08/02: Layout is incorrect. Refer screenshot ADA 08/09: We have fixed the layout now. Kindly retest. QA 08/10: Retest Partially Pass. Layout is correct as per the screenshot. But, the field "Record ID" is now getting populated as "Contraceptive Copay Strategy-Max Supply" Refer Screenshot ETQA 08/10: Closed as per AD comments | Closed | System Test | 2 - Medium
D-01823 | Observation#10:218828:Â CR#1418-Part2-Story#5-Create a Crosswalk Table to Map Max Supply Provision LVs to the Copay Strategy Option | HMO Medical | Line Value Text field should auto-populate. | Line Value Text field is NOT getting auto-populated.Â Test data: MS-07480 ETQA 08/06: Raised Now ADA 08/07: Fixed QA 08/08: Retest Pass. Closed Test Data: MS-07489 | Closed | Smoke Test | 2 - Medium
D-01824 | Observation#41218824: CR#1418-Part2-Story#2-Enhance CRD Wizard to Process Contraceptive Copay Strategy for New Manual CRDs | Traditional - POS | Alignment of the Warning message in Drug Coverage page Â should be in correct format | Alignment of the Warning message in Drug Coverage page Â is Â not in correct format Test Data: CRD-0943441 ¦ DC-1290699 -Retail Non-Commercial formulary Â -FRM-0012122 Commercial formulary Â -FRM-000031 ETQA 08/16: Raised Now ADA 08/21: Code fixed ETQA 08/21: Retest Yet to Start ETQA 08/22: Retest Pass. Closed ETQA 08/30 : Reopened. A bar is visible. AD 08/31 : It has been customized to accommodate future warning message if any. | Closed | Regression Test | 1 - Low
D-01825 | Observation#23:225980: CR#1418-Part2-Story#7-Enhance CRD Wizard to Process Contraceptive Copay Strategy forExisting CRDs | Medicaid | All the Contraceptive Copay Strategy fields Â should copy from existing CRD | Contraceptive Copay Strategy logic is not applying for cloned CRDs Data: Existing: CRD-0942988 ¦ Cloned CRD: CRD-0943037 ETQA 08/09: Raised Now ADA 08/09: Can you let us know if CRD Cloning was in scope/As a part of which request is CRD cloning in scope? We have made changes only for the DC and DCDL cloning. If yes, we would require a note in the story. Vinod 08/09: please review Observation 23 for now Karim 08/09: Can you please elaborate on Observation#23? Did you clone a manual or an automated CRD? Any of CCS fields/ parts cloned or none of the fields was cloned? ETQA 08/10: This Observation is regarding cloning the manual CRD but CCS related any of the fields are not cloned to the new CRDW Karim 08/10: Based on the requirements captured in Stories #3 and #4 all the newly created field for CCS should be cloned along with the other CRD fields. ADA 08/13: Fixed ETQA 08/13: Retest in progress ETQA08/14: Retest Pass. Closed Test Data: CRD-0943316 | Closed | Smoke Test | 2 - Medium
D-01826 | Observation#42:218824: CR#1418-Part2-Story#2-Enhance CRD Wizard to Process Contraceptive Copay Strategy for New Manual CRDs | Traditional - POS | Apply Limitations is set to "No" when Default Drug Â Group(DCA-0000648) is added back to DCDL Section | Apply Limitations is set to "Blank" when Default Drug Â Group(DCA-0000648) is added back to DCDL Section Test Data: CRD-0943460 ETQA 08/16: Raised Now AD 08/16: Â Invalid. For Provision 5 multi month Line values, thereâ€™s no mapping values in the system which states to set Apply Limitations to â€˜Noâ€™ for DCA-0000648 Drug Group.Â ETQA 08/17: Business should confirm on this Business 08/17: Observation#42 needs a code fixÂ ADA08/20: Fixed ETQA08/21: Retest Pass Test Data: CRD-0942410 DC-1288556 ¦ DCDL-45804786 DC-1288558 ¦ DCDL-45804916 | Closed | System Test | 2 - Medium
D-01827 | Observation#22:218825: CR#1418-Part2-Story#3-Add New Fields on Drug Coverage Drug List (DCDL) | HMO - EPOs | As per requirements Steps 1 to Step 12 and Multiplier1 to Multiplier12 fields should have read only Â access | Steps 1 to Step 12 and Multiplier1 to Multiplier12 fields in DCDL section having Â Edit Access Test Data: CRD-0942958 ¦ DC-1289712 ¦ DCDL-45747127 ETQA 08/09: Raised Now ADA 08/09: Fixed QA 08/10: Retest Pass | Closed | System Test | 2 - Medium
D-01828 | Observation#54:225980: CR#1418-Part2-Story#7-Enhance CRD Wizard to Process Contraceptive Copay Strategy for Updating Existing CRDs | Medicaid | As per the requirement, system should display the following error message The Contraceptive Copay Strategy field cannot be set to Applies on the DCDL if the field Does Contraceptive Copay Strategy Apply? is set to No on Drug Coverage | User is getting the below error message The Contraceptive Copay Strategy field cannot be set to Applies on the DCDL if the field Does Contraceptive Copay Strategy Apply is set to No on Drug Coverage Steps to recreate: - Create a DC record with â€œDoes Contraceptive Copay Strategy Apply? as â€œNoâ€ - Click on New DC Drug List/Group and create a DCDL record with Contraceptive Copay Strategy as â€œAppliesâ€ ETQA 08/24: Raised Now ADA 08/27: Fixed ETQA 08/27: 'the' is missing in the error message ADA 08/27: Fixed ETQA 08/27: Retest Pass | Closed | System Test | 1 - Low
D-01829 | Observation#30:218824: CR#1418-Part2-Story#2-Enhance CRD Wizard to Process Contraceptive Copay Strategy for New Manual CRDs | Traditional - HNO | Below Fields Â should Â updated with Mapping values of provision 5 line values in DCDL sectionÂ Inclusion/ExclusionÂ Inclusion/Exclusion Drug Class Apply Limitations | Below Fields Â not Â updated with Mapping values of provision 5 line values in DCDL sectionÂ Inclusion/ExclusionÂ Inclusion/Exclusion Drug Class Apply Limitations Test Data: CRD-0943280 ¦ Provision 5 Line Value - 197 | Closed | System Test | 2 - Medium
D-01830 | Observation#55:218823: CR#1418-Part2-Story#1-Enhance CRD Builder Process to Support Contraceptive Copay | Traditional - PPO | CBON should NOT get processed and user should get the same fallout message in Build Stage | CBON is getting processed till Build Stage and user is NOT getting the same fallout message Test Data: CBON-568471 ¦ FC: 04395352 Steps to recreate: - Create a CBON with below fallout "Max Supply Provision needs to be updated for the Contraceptive Copay Strategy to continue coding the CRD." P5LV199 - Contraceptive Copay Strategy - Applies P6LV123 - There is no active entry in (CCS-Max Supply Crosswalk) - Click on Continue Automation without creating a valid entry in Contraceptive Copay strategy - Max Supply crosswalk ETQA 08/24: Raised Now ADA 08/28: Fixed ETQA 08/28: Retest Pass. Closed Test Data: CBON-568704 ¦ FC: 04395661 | Closed | Smoke Test | 1 - Low
D-01831 | Observation#16:218825: CR#1418-Part2-Story#3-Add New Fields on Drug Coverage Drug List (DCDL) | HMO - EPOs | Contraceptive Copay Strategy Option xmltag should not display in CRDXML file | Contraceptive Copay Strategy Option xmltag is displaying in CRDXML file <Contraceptivecopaystrategy>CCS-00001</Contraceptivecopaystrategy> Test Data: CRD-0942857 CRD-0942857.xml ETQA 08/07: Raised Now ADA 08/07: Fixed Components modified: GMF_XML_CRD_controller QA 08/07: Retest Pass. Closed Test Data: CRD-0942937 | Closed | Regression Test | 2 - Medium
D-01832 | Observation#1:218823: CR#1418-Part2-Story#1-Enhance CRD Builder Process to Support Contraceptive Copay | Traditional - HNO | CRD should get created successfully | CRD is NOT getting created successfully Test data: CBON-567234Â ETQA 08/01: Raised Now ADA 08/02: Fixed QA 08/02: Retest Pass Test Data: CBON-567465 Â | Closed | System Test | 3 - High
D-01833 | Observation#2: 218823: CR#1418-Part2-Story#1-Enhance CRD Builder Process to Support Contraceptive Copay | Traditional - PPO | CRD should get created with formulary | CRD is created without formulary Test data: CBON-567236Â ETQA 08/01: Raised Now ADA 08/02: Fixed QA 08/02: Retest Pass Test Data: CBON-567465 | Closed | System Test | 2 - Medium
D-01834 | Observation#21:218823: CR#1418-Part2-Story#1-Enhance CRD Builder Process to Support Contraceptive Copay | Traditional - HNO | Notes section needs to be update with Drug List and Inclusion Exclusion Drug Class like below for Retail and Mail records DL-0001417 - Contraceptives- emergency | Notes section is incorrectly updated like below for Retail and Mail records DL-0001417's Id ETQA 08/09: Raised Now ADA 08/09: Fixed ETQA 08/10: Retest Pass. Closed | Closed | System Test | 2 - Medium
D-01835 | Observation#55:218823: CR#1418-Part2-Story#1-Enhance CRD Builder Process to Support Contraceptive Copay | Traditional - PPO | CBON should NOT get processed and user should get the same fallout message in Build Stage | CBON is getting processed till Build Stage and user is NOT getting the same fallout message Test Data: CBON-568471 ¦ FC: 04395352 Steps to recreate: - Create a CBON with below fallout "Max Supply Provision needs to be updated for the Contraceptive Copay Strategy to continue coding the CRD." P5LV199 - Contraceptive Copay Strategy - Applies P6LV123 - There is no active entry in (CCS-Max Supply Crosswalk) - Click on Continue Automation without creating a valid entry in Contraceptive Copay strategy - Max Supply crosswalk ETQA 08/24: Raised Now ADA 08/28: Fixed ETQA 08/28: Retest Pass. Closed Test Data: CBON-568704 ¦ FC: 04395661 | Closed | Smoke Test | 1 - Low
D-01836 | Observation#16:218825: CR#1418-Part2-Story#3-Add New Fields on Drug Coverage Drug List (DCDL) | HMO - EPOs | Contraceptive Copay Strategy Option xmltag should not display in CRDXML file | Contraceptive Copay Strategy Option xmltag is displaying in CRDXML file <Contraceptivecopaystrategy>CCS-00001</Contraceptivecopaystrategy> Test Data: CRD-0942857 CRD-0942857.xml ETQA 08/07: Raised Now ADA 08/07: Fixed Components modified: GMF_XML_CRD_controller QA 08/07: Retest Pass. Closed Test Data: CRD-0942937 | Closed | Regression Test | 2 - Medium
D-01837 | Observation#1:218823: CR#1418-Part2-Story#1-Enhance CRD Builder Process to Support Contraceptive Copay | Traditional - HNO | CRD should get created successfully | CRD is NOT getting created successfully Test data: CBON-567234Â ETQA 08/01: Raised Now ADA 08/02: Fixed QA 08/02: Retest Pass Test Data: CBON-567465 Â | Closed | System Test | 3 - High
D-01838 | Observation#2: 218823: CR#1418-Part2-Story#1-Enhance CRD Builder Process to Support Contraceptive Copay | Traditional - PPO | CRD should get created with formulary | CRD is created without formulary Test data: CBON-567236Â ETQA 08/01: Raised Now ADA 08/02: Fixed QA 08/02: Retest Pass Test Data: CBON-567465 | Closed | System Test | 2 - Medium
D-01839 | Observation#40:218825: CR#1418-Part2-Story#3-Add New Fields on Drug Coverage Drug List(DCDL) | HMO - EPOs | DC Record should get updated when other field values are edited | User is getting the below error message and user is NOT able to save the DC record Error message: Error: Invalid Data.Â Review all error messages below to correct your data. Contraceptive Copay Strategy Apply : Field is required Steps to recreate: Create a CRD with Drug Coverage record Open the DC record in Standard layout screen and edit the Override Refill Too Soon? field value Click on Save button ETQA 08/16: Raised Now ETQA 08/20: Need to be discussed in Today's Triage Triage 08/20: Needs to be discussed in Grooming call ADA 08/21: â€˜Does the contraceptive apply?â€™ field validation has been removed as discussed in grooming. For wizard validation rule we are waiting for Jenniferâ€™s comments. Business 08/22: Requirement updated ETQA 08/22: Retest Pass | Closed | System Test | 2 - Medium
D-01840 | Observation#26:218823: CR#1418-Part2-Story#1-Enhance CRD Builder Process to Support Contraceptive Copay | Traditional - HNO | Does Contraceptive Copay Strategy Apply? field value should be populated as "No" | Does Contraceptive Copay Strategy Apply? field value should be populated as BLANK Test Data: CBON-567666 ¦ CRD-0943128 ¦ Provision 5 Line Value 179 ETQA 08/10: Raised Now ADA 08/10: Obsevation#26 has been fixed. ETQA 08/10: Retest Pass. Closed Test Data: CBON-567666 | Closed | System Test | 3 - High
D-01841 | Observation#33:218824: CR#1418-Part2-Story#2-Enhance CRD Wizard to Process Contraceptive Copay Strategy for New Manual CRDs | Traditional - POS | Does Contraceptive Copay Strategy Apply Â values as "No" in standard layout pages then below fields are Â should not allow the user to populate values Provision 5 Line Value Max Supply Provision Max Supply Line Value | When Â user enter the Does Contraceptive Copay Strategy Apply Â values as "No" in standard layout pages then below fields are able to populate values Provision 5 Line Value Max Supply Provision Max Supply Line Value ETQA 08/14: Raised Now ETQA 08/14: Karim needs to update the Requirement ETQA 08/14: We have expectation behavior of Â Contraceptive Copay Strategy fields values in Drug coverage Wizard Visual Force and Drug coverage standard layout pages to be sameÂ ADA 08/14: In grooming we have discussed that the fields can be hidden only for visual force pages not for standard layouts. As salesforce doesnâ€™t provide conditional field control on the standard layouts ADA 08/16: Observation#33 has been fixed as per new Acceptance Criteria#12 for Story 7 ADA08/16: Fixed EQA:08/16: Retest Pass Test Data: CRD-0943441 | Closed | System Test | 3 - High
D-01842 | Observation#29:225980: CR#1418-Part2-Story#7-Enhance CRD Wizard to Process Contraceptive Copay Strategy forExisting CRDs | Medicaid | Does the Contraceptive Copay Strategy Apply Â should set as "No" for all existing CRD as per the requirement | Does the Contraceptive Copay Strategy Apply is set as "Blank" for all existing CRD Test Data: CRD-0942336 ¦ DC-1288411 ¦ DC-1288412 Acceptance Criteria#1: User ability to apply the Program Given that the user has accessed an existing CRD and is on Drug Coverage record in edit mode When the user updates the field "Does the Contraceptive Copay Strategy Apply?" from 'No' to 'Yes' Then the system should display and require user to populate the following fields: 1. Provision 5 Line Value 2. Max Supply Provision 3. Max Supply Line Value ETQA 08/13: Raised Now Vinod 08/13: Karim â€“ can you please confirm requirement for observation #29? ETQA08/14: Waiting for Karim's update for the Story 7 Karim 08/20: Requirement has been updated | Closed | Smoke Test | 2 - Medium
D-01843 | Observation#3:218824: CR#1418-Part2-Story#2-Enhance CRD Wizard to Process Contraceptive Copay Strategy for New Manual CRDs | Traditional - HNO | Drug Coverage record should get created in Wizard screen | Drug Coverage record is NOT getting Â created in Wizard screen. refer the screenshot Test data: CRD-0942544 ETQA 08/01: Raised Now ADA 08/02: Fixed QA 08/02: Retest Pass Test Data: CRD-0942880 ¦ DC-1289554 | Closed | System Test | 2 - Medium
D-01844 | Observation#4:218823: CR#1418-Part2-Story#1-Enhance CRD Builder Process to Support Contraceptive Copay | Traditional - PPO | Drug Coverage record should get created in Wizard screen | Drug Coverage record is NOT getting Â created in Wizard screen. Refer the screenshot ETQA 08/01: Raised Now Aditya 08/03: We are done with the Provision 5 Mapping data load in UAT.Â Please proceed. QA 08/06: Retest - Partially Pass. The below New LV's are NOT loaded in the system 200, 222, 223 ADA 08/07: In progress ADA 08/10: LV224 has been loaded to the system QA 08/10: Retest Pass. Closed ETQA & QA 08/30:Â Expected Result:Â â€¢ Drug List, â€œDL-0016570â€ - Notes section should be updated as â€œDL-0016570 - HCR- Contraceptive coverage Standardâ€ for Provision 5 line values 197, 198, 199, 202, 203, 204, 205, 206, 207, 208, 209, 211, 219, 222, 223, 224 -Fixed. â€¢ Drug Group â€œDCA-0000648â€ - Notes section should be updated as â€œDCA-0000648 - Contraceptives- all drugs and devices (Covered)â€ for Provision 5 line values 197, 198, 199, 202, 203, 204, 205, 206, 207, 208, 209, 211, 219, 222, 223, 224-Fixed. â€¢ Drug List â€œDL-0109016â€ â€“ Notes section should be updated as â€œDL-0109016 - HCR- Contraceptive coverage Standard PLUS 12 month supplyâ€ for Provision 5 line value 199 -Already this is the result Actual Result: â€¢ Drug List, â€œDL-0016570â€ - Notes section is updated as â€œDCA-0000648 - Contraceptives- all drugs and devices (Covered)â€ incorrectly for Provision 5 line values 197, 198, 199, 202, 203, 204, 205, 206, 207, 208, 209, 211, 219, 222, 223, 224 â€¢ Drug Group â€œDCA-0000648â€ - Notes section is updated as â€œDL-0016570 - HCR- Contraceptive coverage Standardâ€ incorrectly for Provision 5 line values 197, 198, 199, 202, 203, 204, 205, 206, 207, 208, 209, 211, 219, 222, 223, 224 â€¢ Drug List â€œDL-0109016â€ â€“ Notes section is updated as â€œDL-0118427 - HCR- Contraceptive Standard, WITH coverage of male condoms $0 after DED-12 monthâ€ incorrectly for Provision 5 line value 199 ETQA 08/31:Â Expected:Â â€¢ Drug List â€œDL-0109016â€ â€“ Notes section should be updated as â€œDL-0109016 - HCR- Contraceptive coverage Standard PLUS 12 month supplyâ€ for Provision 5 line value 199 -Already this is the result â€“In mail record (MV-0370269) â€¢ DL-0016570 â€“ Notes should be updated as â€œDL-0016570 - HCR- Contraceptive coverage Standardâ€ Actual: â€¢ Drug List â€œDL-0109016â€ â€“ Notes section is updated as â€œDL-0118427 - HCR- Contraceptive Standard, WITH coverage of male condoms $0 after DED-12 monthâ€ for Provision 5 line value 199 -Already this is the result â€“ In mail record (MV-0370269) â€¢ DL-0016570 â€“ Notes should be updated as â€œDL-0016570 - HCR - Contraceptive coverage Standardâ€ (Space before Â â€˜-â€˜ and there is 2 space after the â€˜-â€˜) ADA 08/31: Fixed ETQA 08/31: Retest Pass. Closed | Closed | Smoke Test | 2 - Medium
D-01845 | Observation#44:218824: CR#1418-Part2-Story#2-Enhance CRD Wizard to Process Contraceptive Copay Strategy for New Manual CRDs | Traditional - POS | Error Â message Â should display as per requirement Â below Set the field 'Does the Contraceptive Copay Strategy Apply?' to No or update the field 'Provision 5 Line Value' to continue Â | Error Â message Â is displaying Â as below in both pages Set the field Does the Contraceptive Copay Strategy Apply? to No or update the field Provision 5 Line Value to continue ETQA 08/17: Raised Now AD 08/20: Fixed the Code ETQA 08/20: Retest Pass ETQA 08/21: We are facing Error in Wizard Drug coverage screen when click save next button Â as below, Record ID :Cannot specify id in an insert call AD 08/21: Fixed the ObservationÂ ETQA 08/21: Retest Pass | Closed | System Test | 1 - Low
D-01846 | Observation#12,14,15:218823: CR#1418-Part2-Story#1-Enhance CRD Builder Process to Support Contraceptive Copay Strategy | Traditional - PPO | Observation#12: Drug Group - a0f50000000QkkwAAC -DCA-0000648Â Drug List - Â -a0i50000002qLR6AAM -DL-0016570 Observation#14: 1) Apply Limitations should get populated as "Yes" for DL-0001425 as per the business template 2) DL-0016570 (MV-0368970) and DCA-0000648 (MV-0368962) mapping values should NOT get populated in mapping values 3) Parent Map Notes fields should be loaded as "Creates Retail/Mail DCDL P5L196" 4) "Contraceptive Copay Strategy" should be 'Applies' for DL-0001417 (MV-0368971) Observation#15: 1) For Retail Network, Inclusion Exclusion Drug Class should get populated as HCR- Contraceptive coverage Standard PLUS 12 month supply 2) For Mail Network, the below mapping values should get populated Drug List -> DL-0109016Â Inclusion Exclusion Drug Class -> HCR- Contraceptive coverage Standard PLUS 12 month supply | Drug Group - a0i50000002qLR6AAM -DL-0016570 Drug List - Â -a0f50000000QkkwAAC -DCA-0000648 ETQA 08/06: Raised Now ADA 08/07: Fixed ETQA 08/07:Retest Pass. Closed Observation#14: 1) Apply Limitations is getting populated as "No" for DL-0001425 in mapping values 2) DL-0016570 (MV-0368970) and DCA-0000648 (MV-0368962) mapping values is getting populated extra 3) Parent Map Notes fields is loaded as "Creates Retail/Mail DCDL P5L188" 4) "Contraceptive Copay Strategy" is blank for DL-0001417 (MV-0368971 ETQA 08/07: Raised Now ADA 08/07: 1.Fixed. 3.Fixed. 4.Fixed. 2.Invalid. It is handled by code. QA 08/07:Â Retest Pass for 1, 3, and 4 Retest fail for 2 - Waiting for Code fix ETQA 08/13: Retest Pass. Closed Observation#15: 1) For Retail Network, Inclusion Exclusion Drug Class is getting populated as HCR- Contraceptive Standard, WITH coverage of male condoms $0 after DED-12 month 2) For Mail Network, the below mapping values are getting populated Drug List -> DL-0109016 Inclusion Exclusion Drug Class -> HCR- Contraceptive coverage Standard PLUS 12 month supply ETQA 08/07: Raised Now ADA 08/07: Fixed QA 08/07: Retest Pass. Closed | Closed | System Test | 2 - Medium
D-01847 | Observation#20,25:218823: CR#1418-Part2-Story#1-Enhance CRD Builder Process to Support Contraceptive Copay | Traditional - HNO | Observation#20: The mentioned Provision 5, Line value text should be populated as per the business template Observation#25: - DL-0125442 - HCR- Contraceptive coverage Standard PLUS WITH coverage of male condoms - 12 mo The above Drug list and Â Inclusion Exclusion Drug Class should get populated as per the business template | Observation#20: The below text is missing at the end of the text for the mentioned Line value L198 - S ONLY) L205 - Â ONLY) L208 - Â HSA HDHP MANDATE PLANS ONLY) ETQA 08/09: Raised Now ADA 08/09: Invalid. The maximum field length is 255 characters. The Line Value Text is truncated by Salesforce to fit the 255 character width. Jennifer 08/14: Iâ€™ve attached an updated version of the P5 template. Â This reflects the updated LV text for LV198, LV205 and LV208. Karim 08/15: RRC has been updated with the new version. ADA 08/16: The Line Value Texts for the 3 LVs have been updated QA 08/16: Retest Pass. Closed Observation#25: - DL-0125816 - HCR- Contraceptive coverage Expanded PLUS 6 month supply The above Drug list and Â Inclusion Exclusion Drug Class is getting populated in the system ETQA 08/10: Raised Now ADA 08/10: Fixed ETQA 08/10: Retest Pass. Closed | Closed | System Test | 2 - Medium
D-01848 | Observation#7,8:218827: CR#1418-Part2-Story#4-Update Drug Coverage with New Fields | HMO Commercial | Observation#7 Drug Coverage screen, New fields should get populated without wrapping the text at right side of the Drug Coverage details section Observation#8 Provision 5 Line Value should be populated as per the Mockup screen | Observation#7 Drug Coverage screen new fields are getting populated as wrapped text. Refer the screenshot ETQA 08/02: Raised Now Aditya 08/02: Observation#06, 07, 08 are fixed in UAT. Please proceed. ETQA 08/02: Retest Pass Observation#8 Provision 5 LineValue is getting populated in DC screen | Closed | Smoke Test | 1 - Low
D-01849 | Observation#4:218823: CR#1418-Part2-Story#1-Enhance CRD Builder Process to Support Contraceptive Copay | Traditional - PPO | Drug Coverage record should get created in Wizard screen | Drug Coverage record is NOT getting Â created in Wizard screen. Refer the screenshot ETQA 08/01: Raised Now Aditya 08/03: We are done with the Provision 5 Mapping data load in UAT.Â Please proceed. QA 08/06: Retest - Partially Pass. The below New LV's are NOT loaded in the system 200, 222, 223 ADA 08/07: In progress ADA 08/10: LV224 has been loaded to the system QA 08/10: Retest Pass. Closed ETQA & QA 08/30:Â Expected Result:Â â€¢ Drug List, â€œDL-0016570â€ - Notes section should be updated as â€œDL-0016570 - HCR- Contraceptive coverage Standardâ€ for Provision 5 line values 197, 198, 199, 202, 203, 204, 205, 206, 207, 208, 209, 211, 219, 222, 223, 224 -Fixed. â€¢ Drug Group â€œDCA-0000648â€ - Notes section should be updated as â€œDCA-0000648 - Contraceptives- all drugs and devices (Covered)â€ for Provision 5 line values 197, 198, 199, 202, 203, 204, 205, 206, 207, 208, 209, 211, 219, 222, 223, 224-Fixed. â€¢ Drug List â€œDL-0109016â€ â€“ Notes section should be updated as â€œDL-0109016 - HCR- Contraceptive coverage Standard PLUS 12 month supplyâ€ for Provision 5 line value 199 -Already this is the result Actual Result: â€¢ Drug List, â€œDL-0016570â€ - Notes section is updated as â€œDCA-0000648 - Contraceptives- all drugs and devices (Covered)â€ incorrectly for Provision 5 line values 197, 198, 199, 202, 203, 204, 205, 206, 207, 208, 209, 211, 219, 222, 223, 224 â€¢ Drug Group â€œDCA-0000648â€ - Notes section is updated as â€œDL-0016570 - HCR- Contraceptive coverage Standardâ€ incorrectly for Provision 5 line values 197, 198, 199, 202, 203, 204, 205, 206, 207, 208, 209, 211, 219, 222, 223, 224 â€¢ Drug List â€œDL-0109016â€ â€“ Notes section is updated as â€œDL-0118427 - HCR- Contraceptive Standard, WITH coverage of male condoms $0 after DED-12 monthâ€ incorrectly for Provision 5 line value 199 ETQA 08/31:Â Expected:Â â€¢ Drug List â€œDL-0109016â€ â€“ Notes section should be updated as â€œDL-0109016 - HCR- Contraceptive coverage Standard PLUS 12 month supplyâ€ for Provision 5 line value 199 -Already this is the result â€“In mail record (MV-0370269) â€¢ DL-0016570 â€“ Notes should be updated as â€œDL-0016570 - HCR- Contraceptive coverage Standardâ€ Actual: â€¢ Drug List â€œDL-0109016â€ â€“ Notes section is updated as â€œDL-0118427 - HCR- Contraceptive Standard, WITH coverage of male condoms $0 after DED-12 monthâ€ for Provision 5 line value 199 -Already this is the result â€“ In mail record (MV-0370269) â€¢ DL-0016570 â€“ Notes should be updated as â€œDL-0016570 - HCR - Contraceptive coverage Standardâ€ (Space before Â â€˜-â€˜ and there is 2 space after the â€˜-â€˜) ADA 08/31: Fixed ETQA 08/31: Retest Pass. Closed | Closed | Smoke Test | 2 - Medium
D-01850 | Observation#44:218824: CR#1418-Part2-Story#2-Enhance CRD Wizard to Process Contraceptive Copay Strategy for New Manual CRDs | Traditional - POS | Error Â message Â should display as per requirement Â below Set the field 'Does the Contraceptive Copay Strategy Apply?' to No or update the field 'Provision 5 Line Value' to continue Â | Error Â message Â is displaying Â as below in both pages Set the field Does the Contraceptive Copay Strategy Apply? to No or update the field Provision 5 Line Value to continue ETQA 08/17: Raised Now AD 08/20: Fixed the Code ETQA 08/20: Retest Pass ETQA 08/21: We are facing Error in Wizard Drug coverage screen when click save next button Â as below, Record ID :Cannot specify id in an insert call AD 08/21: Fixed the ObservationÂ ETQA 08/21: Retest Pass | Closed | System Test | 1 - Low
D-01851 | Observation#56:218823: CR#1418-Part2-Story#1-Enhance CRD Builder Process to Support Contraceptive Copay | Traditional - PPO | Fallout case should be updated with Multimonth logic Fallout Error: Max Supply Provision needs to be updated for the Contraceptive Copay Strategy to continue coding the CRD. | CBON is processed till Build stage and There is no updated error message based on Multimonth Test Data: CBON-568524 ¦ FC: 04395439 ¦ P6L5 which is inactive in CCS-Max Supply crosswalk Steps to recreate: - Create a CBON with Sensitive Client Build stage fallout - Click on Continue Automation ETQA 08/24: Raised Now ADA 08/28: Fixed ETQA 08/28: Retest Pass. Closed Test Data: CBON-568710 ¦ FC: 04395662 | Closed | Regression Test | 3 - High
D-01852 | Observation#19:218829: CR#1418-Part2-Story#6-Create a Crosswalk Table to Map the Copay Strategy Options to the Option Details | Medicare - Part D | field "Key" shouldn't be displayed on the screen.Â | field "Key" is displayed on the screen. Test data: CCS-11005 ETQA 08/07: Raised Now ADA 08/07: FixedÂ QA 08/07: Retest pass. Closed | Closed | System Test | 2 - Medium
D-01853 | Observation#6:218828: CR#1418-Part2-Story#5-Create a Crosswalk Table to Map Max Supply Provision LVs to the Copay Strategy Option | HMO Medical | Line Value Text, Drug List Name, Active, Comment - fields should be available in the Contraceptive Copay Strategy-Max Supply table | Line Value Text, Drug List Name, Active, Comment - fields are NOT available in the Contraceptive Copay Strategy-Max Supply table ETQA 08/02: Raised Now Aditya 08/02: Observation#06, 07, 08 are fixed in UAT. Please proceed. ETQA 08/02: Layout is incorrect. Refer screenshot ADA 08/09: We have fixed the layout now. Kindly retest. QA 08/10: Retest Partially Pass. Layout is correct as per the screenshot. But, the field "Record ID" is now getting populated as "Contraceptive Copay Strategy-Max Supply" Refer Screenshot ETQA 08/10: Closed as per AD comments | Closed | System Test | 2 - Medium
D-01854 | Observation#10:218828:Â CR#1418-Part2-Story#5-Create a Crosswalk Table to Map Max Supply Provision LVs to the Copay Strategy Option | HMO Medical | Line Value Text field should auto-populate. | Line Value Text field is NOT getting auto-populated.Â Test data: MS-07480 ETQA 08/06: Raised Now ADA 08/07: Fixed QA 08/08: Retest Pass. Closed Test Data: MS-07489 | Closed | Smoke Test | 2 - Medium
D-01855 | Observation#41218824: CR#1418-Part2-Story#2-Enhance CRD Wizard to Process Contraceptive Copay Strategy for New Manual CRDs | Traditional - POS | Alignment of the Warning message in Drug Coverage page Â should be in correct format | Alignment of the Warning message in Drug Coverage page Â is Â not in correct format Test Data: CRD-0943441 ¦ DC-1290699 -Retail Non-Commercial formulary Â -FRM-0012122 Commercial formulary Â -FRM-000031 ETQA 08/16: Raised Now ADA 08/21: Code fixed ETQA 08/21: Retest Yet to Start ETQA 08/22: Retest Pass. Closed ETQA 08/30 : Reopened. A bar is visible. AD 08/31 : It has been customized to accommodate future warning message if any. | Closed | Regression Test | 1 - Low
D-01856 | Observation#23:225980: CR#1418-Part2-Story#7-Enhance CRD Wizard to Process Contraceptive Copay Strategy forExisting CRDs | Medicaid | All the Contraceptive Copay Strategy fields Â should copy from existing CRD | Contraceptive Copay Strategy logic is not applying for cloned CRDs Data: Existing: CRD-0942988 ¦ Cloned CRD: CRD-0943037 ETQA 08/09: Raised Now ADA 08/09: Can you let us know if CRD Cloning was in scope/As a part of which request is CRD cloning in scope? We have made changes only for the DC and DCDL cloning. If yes, we would require a note in the story. Vinod 08/09: please review Observation 23 for now Karim 08/09: Can you please elaborate on Observation#23? Did you clone a manual or an automated CRD? Any of CCS fields/ parts cloned or none of the fields was cloned? ETQA 08/10: This Observation is regarding cloning the manual CRD but CCS related any of the fields are not cloned to the new CRDW Karim 08/10: Based on the requirements captured in Stories #3 and #4 all the newly created field for CCS should be cloned along with the other CRD fields. ADA 08/13: Fixed ETQA 08/13: Retest in progress ETQA08/14: Retest Pass. Closed Test Data: CRD-0943316 | Closed | Smoke Test | 2 - Medium
D-01857 | Observation#42:218824: CR#1418-Part2-Story#2-Enhance CRD Wizard to Process Contraceptive Copay Strategy for New Manual CRDs | Traditional - POS | Apply Limitations is set to "No" when Default Drug Â Group(DCA-0000648) is added back to DCDL Section | Apply Limitations is set to "Blank" when Default Drug Â Group(DCA-0000648) is added back to DCDL Section Test Data: CRD-0943460 ETQA 08/16: Raised Now AD 08/16: Â Invalid. For Provision 5 multi month Line values, thereâ€™s no mapping values in the system which states to set Apply Limitations to â€˜Noâ€™ for DCA-0000648 Drug Group.Â ETQA 08/17: Business should confirm on this Business 08/17: Observation#42 needs a code fixÂ ADA08/20: Fixed ETQA08/21: Retest Pass Test Data: CRD-0942410 DC-1288556 ¦ DCDL-45804786 DC-1288558 ¦ DCDL-45804916 | Closed | System Test | 2 - Medium
D-01858 | Observation#4:218823: CR#1418-Part2-Story#1-Enhance CRD Builder Process to Support Contraceptive Copay | Traditional - PPO | Drug Coverage record should get created in Wizard screen | Drug Coverage record is NOT getting Â created in Wizard screen. Refer the screenshot ETQA 08/01: Raised Now Aditya 08/03: We are done with the Provision 5 Mapping data load in UAT.Â Please proceed. QA 08/06: Retest - Partially Pass. The below New LV's are NOT loaded in the system 200, 222, 223 ADA 08/07: In progress ADA 08/10: LV224 has been loaded to the system QA 08/10: Retest Pass. Closed ETQA & QA 08/30:Â Expected Result:Â â€¢ Drug List, â€œDL-0016570â€ - Notes section should be updated as â€œDL-0016570 - HCR- Contraceptive coverage Standardâ€ for Provision 5 line values 197, 198, 199, 202, 203, 204, 205, 206, 207, 208, 209, 211, 219, 222, 223, 224 -Fixed. â€¢ Drug Group â€œDCA-0000648â€ - Notes section should be updated as â€œDCA-0000648 - Contraceptives- all drugs and devices (Covered)â€ for Provision 5 line values 197, 198, 199, 202, 203, 204, 205, 206, 207, 208, 209, 211, 219, 222, 223, 224-Fixed. â€¢ Drug List â€œDL-0109016â€ â€“ Notes section should be updated as â€œDL-0109016 - HCR- Contraceptive coverage Standard PLUS 12 month supplyâ€ for Provision 5 line value 199 -Already this is the result Actual Result: â€¢ Drug List, â€œDL-0016570â€ - Notes section is updated as â€œDCA-0000648 - Contraceptives- all drugs and devices (Covered)â€ incorrectly for Provision 5 line values 197, 198, 199, 202, 203, 204, 205, 206, 207, 208, 209, 211, 219, 222, 223, 224 â€¢ Drug Group â€œDCA-0000648â€ - Notes section is updated as â€œDL-0016570 - HCR- Contraceptive coverage Standardâ€ incorrectly for Provision 5 line values 197, 198, 199, 202, 203, 204, 205, 206, 207, 208, 209, 211, 219, 222, 223, 224 â€¢ Drug List â€œDL-0109016â€ â€“ Notes section is updated as â€œDL-0118427 - HCR- Contraceptive Standard, WITH coverage of male condoms $0 after DED-12 monthâ€ incorrectly for Provision 5 line value 199 ETQA 08/31:Â Expected:Â â€¢ Drug List â€œDL-0109016â€ â€“ Notes section should be updated as â€œDL-0109016 - HCR- Contraceptive coverage Standard PLUS 12 month supplyâ€ for Provision 5 line value 199 -Already this is the result â€“In mail record (MV-0370269) â€¢ DL-0016570 â€“ Notes should be updated as â€œDL-0016570 - HCR- Contraceptive coverage Standardâ€ Actual: â€¢ Drug List â€œDL-0109016â€ â€“ Notes section is updated as â€œDL-0118427 - HCR- Contraceptive Standard, WITH coverage of male condoms $0 after DED-12 monthâ€ for Provision 5 line value 199 -Already this is the result â€“ In mail record (MV-0370269) â€¢ DL-0016570 â€“ Notes should be updated as â€œDL-0016570 - HCR - Contraceptive coverage Standardâ€ (Space before Â â€˜-â€˜ and there is 2 space after the â€˜-â€˜) ADA 08/31: Fixed ETQA 08/31: Retest Pass. Closed | Closed | Smoke Test | 2 - Medium
D-01859 | Observation#44:218824: CR#1418-Part2-Story#2-Enhance CRD Wizard to Process Contraceptive Copay Strategy for New Manual CRDs | Traditional - POS | Error Â message Â should display as per requirement Â below Set the field 'Does the Contraceptive Copay Strategy Apply?' to No or update the field 'Provision 5 Line Value' to continue Â | Error Â message Â is displaying Â as below in both pages Set the field Does the Contraceptive Copay Strategy Apply? to No or update the field Provision 5 Line Value to continue ETQA 08/17: Raised Now AD 08/20: Fixed the Code ETQA 08/20: Retest Pass ETQA 08/21: We are facing Error in Wizard Drug coverage screen when click save next button Â as below, Record ID :Cannot specify id in an insert call AD 08/21: Fixed the ObservationÂ ETQA 08/21: Retest Pass | Closed | System Test | 1 - Low
D-01860 | Observation#12,14,15:218823: CR#1418-Part2-Story#1-Enhance CRD Builder Process to Support Contraceptive Copay Strategy | Traditional - PPO | Observation#12: Drug Group - a0f50000000QkkwAAC -DCA-0000648Â Drug List - Â -a0i50000002qLR6AAM -DL-0016570 Observation#14: 1) Apply Limitations should get populated as "Yes" for DL-0001425 as per the business template 2) DL-0016570 (MV-0368970) and DCA-0000648 (MV-0368962) mapping values should NOT get populated in mapping values 3) Parent Map Notes fields should be loaded as "Creates Retail/Mail DCDL P5L196" 4) "Contraceptive Copay Strategy" should be 'Applies' for DL-0001417 (MV-0368971) Observation#15: 1) For Retail Network, Inclusion Exclusion Drug Class should get populated as HCR- Contraceptive coverage Standard PLUS 12 month supply 2) For Mail Network, the below mapping values should get populated Drug List -> DL-0109016Â Inclusion Exclusion Drug Class -> HCR- Contraceptive coverage Standard PLUS 12 month supply | Drug Group - a0i50000002qLR6AAM -DL-0016570 Drug List - Â -a0f50000000QkkwAAC -DCA-0000648 ETQA 08/06: Raised Now ADA 08/07: Fixed ETQA 08/07:Retest Pass. Closed Observation#14: 1) Apply Limitations is getting populated as "No" for DL-0001425 in mapping values 2) DL-0016570 (MV-0368970) and DCA-0000648 (MV-0368962) mapping values is getting populated extra 3) Parent Map Notes fields is loaded as "Creates Retail/Mail DCDL P5L188" 4) "Contraceptive Copay Strategy" is blank for DL-0001417 (MV-0368971 ETQA 08/07: Raised Now ADA 08/07: 1.Fixed. 3.Fixed. 4.Fixed. 2.Invalid. It is handled by code. QA 08/07:Â Retest Pass for 1, 3, and 4 Retest fail for 2 - Waiting for Code fix ETQA 08/13: Retest Pass. Closed Observation#15: 1) For Retail Network, Inclusion Exclusion Drug Class is getting populated as HCR- Contraceptive Standard, WITH coverage of male condoms $0 after DED-12 month 2) For Mail Network, the below mapping values are getting populated Drug List -> DL-0109016 Inclusion Exclusion Drug Class -> HCR- Contraceptive coverage Standard PLUS 12 month supply ETQA 08/07: Raised Now ADA 08/07: Fixed QA 08/07: Retest Pass. Closed | Closed | System Test | 2 - Medium
D-01861 | Observation#20,25:218823: CR#1418-Part2-Story#1-Enhance CRD Builder Process to Support Contraceptive Copay | Traditional - HNO | Observation#20: The mentioned Provision 5, Line value text should be populated as per the business template Observation#25: - DL-0125442 - HCR- Contraceptive coverage Standard PLUS WITH coverage of male condoms - 12 mo The above Drug list and Â Inclusion Exclusion Drug Class should get populated as per the business template | Observation#20: The below text is missing at the end of the text for the mentioned Line value L198 - S ONLY) L205 - Â ONLY) L208 - Â HSA HDHP MANDATE PLANS ONLY) ETQA 08/09: Raised Now ADA 08/09: Invalid. The maximum field length is 255 characters. The Line Value Text is truncated by Salesforce to fit the 255 character width. Jennifer 08/14: Iâ€™ve attached an updated version of the P5 template. Â This reflects the updated LV text for LV198, LV205 and LV208. Karim 08/15: RRC has been updated with the new version. ADA 08/16: The Line Value Texts for the 3 LVs have been updated QA 08/16: Retest Pass. Closed Observation#25: - DL-0125816 - HCR- Contraceptive coverage Expanded PLUS 6 month supply The above Drug list and Â Inclusion Exclusion Drug Class is getting populated in the system ETQA 08/10: Raised Now ADA 08/10: Fixed ETQA 08/10: Retest Pass. Closed | Closed | System Test | 2 - Medium
D-01862 | Observation#7,8:218827: CR#1418-Part2-Story#4-Update Drug Coverage with New Fields | HMO Commercial | Observation#7 Drug Coverage screen, New fields should get populated without wrapping the text at right side of the Drug Coverage details section Observation#8 Provision 5 Line Value should be populated as per the Mockup screen | Observation#7 Drug Coverage screen new fields are getting populated as wrapped text. Refer the screenshot ETQA 08/02: Raised Now Aditya 08/02: Observation#06, 07, 08 are fixed in UAT. Please proceed. ETQA 08/02: Retest Pass Observation#8 Provision 5 LineValue is getting populated in DC screen | Closed | Smoke Test | 1 - Low
D-01863 | Observation#4:218823: CR#1418-Part2-Story#1-Enhance CRD Builder Process to Support Contraceptive Copay | Traditional - PPO | Drug Coverage record should get created in Wizard screen | Drug Coverage record is NOT getting Â created in Wizard screen. Refer the screenshot ETQA 08/01: Raised Now Aditya 08/03: We are done with the Provision 5 Mapping data load in UAT.Â Please proceed. QA 08/06: Retest - Partially Pass. The below New LV's are NOT loaded in the system 200, 222, 223 ADA 08/07: In progress ADA 08/10: LV224 has been loaded to the system QA 08/10: Retest Pass. Closed ETQA & QA 08/30:Â Expected Result:Â â€¢ Drug List, â€œDL-0016570â€ - Notes section should be updated as â€œDL-0016570 - HCR- Contraceptive coverage Standardâ€ for Provision 5 line values 197, 198, 199, 202, 203, 204, 205, 206, 207, 208, 209, 211, 219, 222, 223, 224 -Fixed. â€¢ Drug Group â€œDCA-0000648â€ - Notes section should be updated as â€œDCA-0000648 - Contraceptives- all drugs and devices (Covered)â€ for Provision 5 line values 197, 198, 199, 202, 203, 204, 205, 206, 207, 208, 209, 211, 219, 222, 223, 224-Fixed. â€¢ Drug List â€œDL-0109016â€ â€“ Notes section should be updated as â€œDL-0109016 - HCR- Contraceptive coverage Standard PLUS 12 month supplyâ€ for Provision 5 line value 199 -Already this is the result Actual Result: â€¢ Drug List, â€œDL-0016570â€ - Notes section is updated as â€œDCA-0000648 - Contraceptives- all drugs and devices (Covered)â€ incorrectly for Provision 5 line values 197, 198, 199, 202, 203, 204, 205, 206, 207, 208, 209, 211, 219, 222, 223, 224 â€¢ Drug Group â€œDCA-0000648â€ - Notes section is updated as â€œDL-0016570 - HCR- Contraceptive coverage Standardâ€ incorrectly for Provision 5 line values 197, 198, 199, 202, 203, 204, 205, 206, 207, 208, 209, 211, 219, 222, 223, 224 â€¢ Drug List â€œDL-0109016â€ â€“ Notes section is updated as â€œDL-0118427 - HCR- Contraceptive Standard, WITH coverage of male condoms $0 after DED-12 monthâ€ incorrectly for Provision 5 line value 199 ETQA 08/31:Â Expected:Â â€¢ Drug List â€œDL-0109016â€ â€“ Notes section should be updated as â€œDL-0109016 - HCR- Contraceptive coverage Standard PLUS 12 month supplyâ€ for Provision 5 line value 199 -Already this is the result â€“In mail record (MV-0370269) â€¢ DL-0016570 â€“ Notes should be updated as â€œDL-0016570 - HCR- Contraceptive coverage Standardâ€ Actual: â€¢ Drug List â€œDL-0109016â€ â€“ Notes section is updated as â€œDL-0118427 - HCR- Contraceptive Standard, WITH coverage of male condoms $0 after DED-12 monthâ€ for Provision 5 line value 199 -Already this is the result â€“ In mail record (MV-0370269) â€¢ DL-0016570 â€“ Notes should be updated as â€œDL-0016570 - HCR - Contraceptive coverage Standardâ€ (Space before Â â€˜-â€˜ and there is 2 space after the â€˜-â€˜) ADA 08/31: Fixed ETQA 08/31: Retest Pass. Closed | Closed | Smoke Test | 2 - Medium
D-01864 | Observation#44:218824: CR#1418-Part2-Story#2-Enhance CRD Wizard to Process Contraceptive Copay Strategy for New Manual CRDs | Traditional - POS | Error Â message Â should display as per requirement Â below Set the field 'Does the Contraceptive Copay Strategy Apply?' to No or update the field 'Provision 5 Line Value' to continue Â | Error Â message Â is displaying Â as below in both pages Set the field Does the Contraceptive Copay Strategy Apply? to No or update the field Provision 5 Line Value to continue ETQA 08/17: Raised Now AD 08/20: Fixed the Code ETQA 08/20: Retest Pass ETQA 08/21: We are facing Error in Wizard Drug coverage screen when click save next button Â as below, Record ID :Cannot specify id in an insert call AD 08/21: Fixed the ObservationÂ ETQA 08/21: Retest Pass | Closed | System Test | 1 - Low
D-01865 | Observation#11:218823: CR#1418-Part2-Story#1-Enhance CRD Builder Process to Support Contraceptive Copay Strategy | Traditional - PPO | Retail& Mail-Maximum Days =180 Â | Retail&Mail-Maximum Days =184 ETQA 08/06: Raised Now ADA 08/07: Fixed ETQA 08/08:Retest Pass. Closed | Closed | System Test | 2 - Medium
D-01866 | Observation#27:CR#1418-Part2-Story#5-Create a Crosswalk Table to Map Max Supply Provision LVs to the Copay Strategy Option | HMO Medical | Standard History Tracking template should be available for the below mentioned fields in Contraceptive Copay Strategy-Max Supply Crosswalk.Â Max Supply Provision Line Value, Plan Type, Drug List ID, Option Name, Active, CommentÂ | Standard History Tracking template is NOT available for the mentioned fields in Contraceptive Copay Strategy-Max Supply Crosswalk. ETQA 08/13: Raised Now ADA 08/13: Fixed ETQA 08/13: Retest - Partially Pass. Standard History Tracking template is not available for "Max Supply Provision Line Value" and "comment" fields. AD 08/13: History tracking for â€˜Max Supply Provision Line Valueâ€™ has been enabled. Comment field is already being tracked. Please check MS-0028 record for reference. ETQA 08/13: Retest Pass | Closed | System Test | 3 - High
D-01867 | Observation#28:218829CR#1418-Part2-Story#6-Create a Crosswalk Table to Map the Copay Strategy Options to the Option Details | Medicare - Part A | Standard History Tracking template should be available for the below mentioned fields in Contraceptive Copay Strategy-Options Crosswalk.Â Fields Option name, steps, multipliers, active and commentsÂ | Standard History Tracking template is NOT available for the mentioned fields in Contraceptive Copay Strategy-Options Crosswalk ETQA 08/13: Raised Now ADA 08/13: Fixed ETQA 08/13: Retest Â Pass. Test data: CCS-11107 | Closed | System Test | 2 - Medium
D-01868 | Observation#48:218829: CR#1418-Part2-Story#6-Create a Crosswalk Table to Map the Copay Strategy Options to the Option Details | Medicare - Part D | Steps & Multipliers should be populated as per the given business crosswalk template CCS-00002 - 1x, 2x, 4x, 6x, 8x CCS-00011 - 1x, 2.5x, 5x, 7.5x, 9x CCS-00014 - 1x, 2x, 3x, 4x, 5x, 6x, 7x, 8x, 9x, 10x, 11x Steps - 1-30 days should not be populated | Steps & Multipliers are populated incorrectly in Contraceptive Copay Strategy -Max Supply CrosswalkÂ CCS-00002 - 1x, 2x, 3x, 4x, 5x CCS-00011 - 1x, 3x, 9x, 12x, 15x CCS-00014 - 1x, 2x, 4x, 6x, 8x, 10x, 12x, 14x, 16x, 18x, 20x, 22x Steps - 1-30 days is available extra ETQA 08/20: Raised Now ADA 08/21: Fixed ETQA 08/21: Retest Pass For CCS-00016 record, Step2 field is incorrect Expected: Step2 -> 181-365 days Actual: Step2 -> 180-365 days ADA 08/21: Fixed ETQA 08/21: Retest Pass. Closed | Closed | System Test | 2 - Medium
D-01869 | Observation#46:218824: CR#1418-Part2-Story#2-Enhance CRD Wizard to Process Contraceptive Copay Strategy for New Manual CRDs | Traditional - POS | System should display the below Â Error Message Â when user populate and save the unmapped provision 5 line value in wizard drug coverage page and Standard Drug coverage page The system cannot process the contraceptive copay strategy for provision 5. Please code the provision 5 details.â€ | System is not display the below Â Error Message Â when user populate and save the unmapped provision 5 line value in wizard drug coverage page and Standard Drug coverage page The system cannot process the contraceptive copay strategy for provision 5. Please code the provision 5 details.â€ Test Data: CRD-0943517 ¦ DC-1290794 ¦ DC-1290796 ETQA 08/17: Raised Now ADA08/21:For Observation#46 we need to update different vf pages. Code drop for same will be done by tomorrow EOD. ETQA 08/23: Retest Pass. Closed | Closed | Regression Test | 1 - Low
D-01870 | Observation#39:218829: CR#1418-Part2-Story#6-Create a Crosswalk Table to Map the Copay Strategy Options to the Option Details | Medicare - Part B | System should stop processing further the CRD Â when Contraceptive Copay Strategy-Options is Inactive in table Â | System is processing the CRD and save the DCDL record with contraceptive Copay Strategy option Test Data: CRD-0942379 ¦ DC-1288495 ¦ DCDL-45783801 ¦ DCDL-45783802 ETQA 08/16: Raised Now AD 08/16: Processing of CRD will only be stopped in case of inactive â€˜Contraceptive copay max supplyâ€™ table records. Please share with us the Acceptance criteria which states stop crd processing in case of inactive â€˜Contraceptive Copay Strategy-Optionsâ€™ record. Jennifer 08/17: Its correct behavior Â to not show steps ,option and multipliers in DCDL section even if Contraceptive copay strategy Â applies when CCS option is inactive. Logic should pick all teh active records AD 08/17: Fixed the records picking Active data ETQA 08/20: Retest Pass. Closed Test Data: CRD-0943575 ¦ DCDL-45795407-Retail ¦ DCDL-45795359-Mail | Closed | System Test | 3 - High
D-01871 | Observation#45:218824: CR#1418-Part2-Story#2-Enhance CRD Wizard to Process Contraceptive Copay Strategy for New Manual CRDs | Traditional - HNO | System should through the Error message as " Max Supply Provision : Field is required" System should through the Error message as " Provision 5 Line Value : Field is required" | System Â is Â displaying wrong error message as below Error: Max Supply Line Value : Field is required System Â is Â displaying wrong error message as below Error: Max Supply Line Value : Field is required 2. When user select Does Contraceptive Copay Strategy Apply as Â "Yes and clicks Â on 'Save button Â in standard Drug Coverage page ETQA 08/17: Raised Now AD 08/20: Fixed the Code ETQA 08/21: Retest Pass | Closed | System Test | 2 - Medium
D-01872 | Observation#57:218823: CR#1418-Part2-Story#1-Enhance CRD Builder Process to Support Contraceptive Copay | Traditional - PPO | The error message should NOT display and CRD should get created | Fallout case is created with the mentioned error message Test Data: CBON-568893 ¦ FC: 04395955 ETQA 08/30: Raised Now ADA 08/31: Fixed ETQA 08/31: Retest Pass. Closed Test Data: CBON-569058 | Closed | System Test | 3 - High
D-01873 | Observation#5:218823: CR#1418-Part2-Story#1-Enhance CRD Builder Process to Support Contraceptive Copay | Traditional - HNO | The fields should be available in the CRD Standard layout screen | The fields are NOT be available in the CRD Standard layout screen ETQA 08/01: Raised Now QA 08/02: Retest Pass Fields are available in DC Standard layout screen | Closed | System Test | 2 - Medium
D-01874 | Observation#38:218829: CR#1418-Part2-Story#6-Create a Crosswalk Table to Map the Copay Strategy Options to the Option Details | Medicare - Part A | User should be able to enter only 4 characters in the "Multipliers" field | User is able to enter more than 4 characters in the "Multipliers" field Test Data:Â CCS-21011 ETQA 08/16: Raised Now ADA 08/17: Fixed after the requirement update and the data type has been modified to Text(6) ETQA 08/17: Retest Pass. Closed. | Closed | System Test | 2 - Medium